## Created By
Revision Number | Revision Date | Summary of Changes | Author(s)
0.1 | 2016-11-29 | Initial revision | Umang Garg, Ronak Shettigar, Devang Sawant, Chaitanya Gadiyam, Rohan Shiroor, Poornima Ubale

## Test Plan_Beta Testing
Test Planner and Tracker |  |  | Group 3 | Bug Biters
Test No. ID | Related Systems / User Story | Pre-conditions | Test Description (steps) | Expected Outcome | R1 Outcome (color code cell background) | R2 beta Outcome (color code cell background) | R2 Outcome (color code cell background)
1 | Registration | 1. System is setup and configured. 2. System is up for registrations. | 1. Go to the Tool share online website 2. Click on the 'Sign Up' link | System should display 'User Registration' page. | Pass
2 | Registration | 1. System is setup and configured. 2. System is up for registrations. | 1. On User Registration page, enter below details: First Name, LastName, Email (mention email format only), Username, Password, Confirm Password, Address Line1, Address Line 2, State, City, Zipcode, Telephone. 2. Click on 'Register' button. | System should display message stating that 'Congratulations, you have successfully registered!'. | Pass
3 | Registration | 1. System is setup and configured. 2. System is up for registrations. 3. Username is already exist | 1. Go to the Tool share online website 2. Click on the 'Sign Up' link 3. First Name, LastName, Email (mention email format only), Username (enter same username as step 2), Password, Confirm Password, Address Line1, Address Line 2, State, City, Zipcode, Telephone. | System should display the message that username is already exists. | Pass Note: Validation is handled by backend for existing user functionality. Front end validation yet to be done.
4 | Registration | 1. System is setup and configured. 2. System is up for registrations. | 1. Go to the Tool share online website 2. Click on the 'Sign Up' link 3. Enter all required registration details and register to the system. | System should display appropriate error message to the user. | Pass
5 | Registration | 1. System is setup and configured. 2. System is up for registrations. 3. Username is already exist | 1. Go to the Tool share online website 2. Click on the 'Sign Up' link 3. First Name, LastName, Email (mention email format only), Username, Password, Confirm Password, Address Line1, Address Line 2, State, City, Zipcode, Telephone. 4. Click on 'Cancel' link. | System should display the login page. | Pass
6 | Community Shed Creation | 1. User must have not registered to the system. 2. Community shed does not exist with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. Click on 'Sign Up' link 3. Enter all registration details and click on 'Register' button | System should display message to the user that user has been registered to the system successfully and should display 'Create Shed' form. | Pass
7 | Community Shed Creation | 1. User must have not registered to the system. 2. Community shed does not exist with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. Click on 'Sign Up' link 3. Enter all registration details and click on 'Register' button 4. User registers to the system 5. Click on 'Create' button. | System should display the success page for create shed. | Pass
8 | Community Shed Creation | 1. User must have not registered to the system. 2. Community shed does not exist with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. Click on 'Sign Up' link 3. Enter all registration details and click on 'Register' button 4. User registers to the system 5. Click on 'Login' button instead of 'Create'. | System should display the Login page and should not create a shed for the corresponding zipcode. It should display Login page. | Pass
9 | Community Shed Creation | 1. User must have registered to the system. 2. Community shed does not exist with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password. | System should display link for create shed on homepage. | Pass
10 | Community Shed Creation | 1. User must have registered to the system. 2. Community shed does not exist with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password. 3. Click on 'Create Shed' link. | System should display create shed form with create and cancel button. | Pass
11 | Community Shed Creation | 1. User must have registered to the system. 2. Community shed does not exist with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password. 3. Click on 'Create Shed' link on homepage 4. Click on 'Cancel' button. | System shouldn't create community shed and should redirect to the homepage. | Pass
12 | Community Shed Creation | 1. User must have registered to the system. 2. Community shed does not exist with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password. 3. Click on 'Create Shed' link on homepage 4. Click on 'Create' button. | System should create a shed successfully. | Pass
13 | View- Created Shed | 1. User must have not registered to the system. 2. Community shed exists with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password. | System should display link for view shed on homepage. | Pass
14 | View- Community Shed | 1. User must have not registered to the system. 2. Community shed exists with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password. 3. Click on view shed link. | System should display shed location details. | Pass
15 | View- Community Shed | 1. User must have not registered to the system. 2. Community shed exists with the corresponding zipcode in the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password. 3. Click on view shed link. 4. Click on 'Back' button. | System should display Homepage. | Pass
16 | Login | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password. | System should redirect the user to the home page. | Pass
17 | Login | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the invalid credentials : Username and Password | System should display an error message stating that 'User Name and/or password does not match our records.' | Pass
18 | Login | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, do not enter 'Username or Password' | System should display an error message stating that 'Please fill out this field'. | Pass
19 | Account Management - Change Personal Information | 1. User must have registered to the system. | 1. Go to Tool share online website 3. On login page, enter the valid credentials : Username and Password 4. On homepage, click on 'Profile' link | System should display 'Update Profile' form with all appropriate user details. | Pass
20 | Account Management - Change Personal Information | 1. User must have registered to the system. | 1. Go to Tool share online website 3. On login page, enter the valid credentials : Username and Password 4. On homepage, click on 'Profile' link 5. Change the user field which user wants to change. For example, First Name, Last Name etc. | System should allow user to edit information and save updated user information in the database. | Pass
21 | Account Management - Change Personal Information | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password 4. On homepage, click on 'Profile' link 5. Remove the existing details and keep the field blank. For example, City, State etc. | System should display appropriate error message to the user. | Pass
22 | Account Management - Change Personal Information | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password 4. On homepage, click on 'Profile' link 5. Click on 'Cancel' link. | System should redirects to the main home page without changing the user details. | Pass
23 | Tool Management: Registration | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password 4. On homepage, click on 'My Tools' tab 5. Click on 'Register Tool' link. | System should display 'My Tools' page. | Pass
24 | Tool Management: Registration | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password 4. On homepage, click on 'My Tools' tab 5. Click on 'Register Tool' link. 6. Enter the details like Name, select the category from dropdown, Description, Upload Picture, and Special Instructions. 7. Click on 'Register' button. | System should store the tool information in the database, and displays the message stating that 'Tool Registered successfully!.' | Passs
25 | Tool Management: Registration | 1. User must have registered to the system. 2. User must be logged into the system 3. Tool must be registered by the user | 1. Click on 'My Tools' tab. 2. Click on 'Shared Tools' tab. | System should displays all user's registered tools. | Pass
26 | Tool Management: Registration | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password 4. On homepage, click on 'My Tools' link 5. Click on 'Register Tool' link. 6. Enter the details like Name, select the category from dropdown, Description, Select location(Share from Home or Share from Community Shed), Upload Picture(image), and Special Instructions. 7. Click on 'Cancel' link. | System should allow user to cancel and should redirect the user to the My Tools page. | Pass
27 | Tool Management: Registration | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials : Username and Password 4. On homepage, click on 'My Tools' link 5. Click on 'Register Tool' link. 6. Do not enter the all fields on tool registration page. 7. Click on 'Register' button. | System should display appropriate error message to the user to enter all required details. Note: Front end validation is yet to be added. | Pass
28 | Sharing - From Community Shed | 1. User must have registered to the system. 2. User(Owner) must have registered the tool and shared location should be 'Community Shed' | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. On homepage, click on My Tool tab 4. Click on Shared Tool tab | System should display list of tools shared by User(Owner) in Community Shed. | Pass
29 | Request tool - From Community Shed | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on 'Borrow' tab | System should display all available tools with status of the tool. | Pass
30 | Request tool - From Community Shed | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on 'Borrow' tab 4. Click on 'View' button. | System should display 'Tool Details' form with 'Borrow' and 'Back' button. | Pass
31 | Request tool - From Community Shed | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on 'Borrow' tab 4. Click on 'View' button. 5. Click on 'Borrow' button. | System should display submit request to borrow tool form. | Pass
32 | Request tool - From Community Shed | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on 'Borrow' tab 4. Click on 'View' button. 5. Click on 'Borrow' button. 6. Add Start date, End date and message and click on 'Submit' button. | System should changed the status of the tool to borrowed and request should be automatically accepted. | Pass
33 | Request tool - From Community Shed | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on 'Borrow' tab 4. Click on 'View' button. 5. Click on 'Borrow' button. 6. Add Start date, End date and message and click on 'Back' button. | System should display all available tools with status of the tool. | Pass
34 | Sharing - From Home | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. On homepage, click on My Tool tab 4. Click on Shared Tool tab | System should display list of tools shared by User(Owner) in Home. | Pass
35 | Request tool - From Home | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on 'Borrow' tab 4. Click on 'View' button. 5. Click on 'Borrow' button. | System should display submit request to borrow tool form. | Pass
36 | Request tool - From Home | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on 'Borrow' tab 4. Click on 'View' button. 5. Click on 'Borrow' button. 6. Add Start date, End date and message and click on 'Submit' button. | System should change the status of the tool to borrowed and should send a request to owner for approval. | Pass
37 | Request tool - From Home | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on Manage Requests tab 4. Click on Accept button. | System should allow User(owner) to accept the borrower request. | Pass
38 | Request tool - From Home | 1. User must have registered to the system. 2. User(Owner) must have registered the tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on Manage Requests tab 4. Click on Reject button. | System should allow User(Owner) to reject the borrower request. | Pass
39 | Borrower-Return Tool | 1. User must have registered to the system. 2. User(Borrower) must have borrowed tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on My Tools tab 4. Click on 'Return Tool' link. | System should display 'Tool Return' Form. | Pass
40 | Borrower-Return Tool | 1. User must have registered to the system. 2. User(Borrower) must have borrowed tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on My Tools tab 4. Click on 'Return Tool' link. 5. Add Comment and click on 'Submit' button. | System should display message stating that Tool return request sent to the owner. | Pass
41 | Borrower-Return Tool | 1. User(Borrower) must have registered to the system. 2. User(Borrower) must have borrowed tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Borrower) : Username and Password 3. On homepage, click on My Tools tab 4. Click on 'Return Tool' link. 5. Add Comment and click on Cancel button. | System should cancel the return request. | Pass
42 | Owner-Return Tool | 1. User must have registered to the system. 2. User(Borrower) must have returned the borrowed tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. On homepage, click on Manage Requests tab | System should display Manage Tool Borrow Request page. | Pass
43 | Owner-Return Tool | 1. User must have registered to the system. 2. User(Borrower) must have returned the borrowed tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. On homepage, click on Manage Requests tab 4. Verify the returned tool status has been changed to the 'Released' | System should display the status as 'Released' to the owner | Pass
44 | Owner-Return Tool | 1. User must have registered to the system. 2. User(Borrower) must have returned the borrowed tool. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. On homepage, click on Manage Requests tab 4. Click on 'Accept' action link. | System should allow user(owner) to change the status to 'Complete'. | Pass
45 | View Feedback | 1. User must have registered to the system. 2. User(Borrower) must have returned the returned the tool. 3. User(Owner) must have updated the status in the system as accepted | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. On homepage, click on Manage Requests tab 4. Click on 'View Feedback' action link. | System should display the feedback to owner about the tool which has been provided by the borrower. | Pass
46 | View Feedback | 1. User must have registered to the system. 2. User(Borrower) must have returned the returned the tool. 3. User(Owner) must have updated the status in the system as accepted | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. On homepage, click on Manage Requests tab 4. Click on 'View Feedback' action link. 5. Click on 'Back' link. | System should display Manage Tool Borrow Request page. | Pass
47 | Tool Management - Status | 1. User(Owner) must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. Go to 'My Tools' of 'Shared Tools' tab. | System should display shared tools by the owner with status and action. | Pass
48 | Tool Management - deactivation and reactivation | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. Go to 'My Tools' of 'Shared Tools' tab. 4. Click on 'Deactivate' link | System should change the status of the tool to deactivated and deactivated tool is not displayed in borrowed list. | Pass
49 | Tool Management - deactivation and reactivation | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. Go to 'My Tools' of 'Shared Tools' tab., select the 'Tool' which user wants to deactivate. 5. Verify that user not able to see the deactivated tool. | After deactivation of tool, tool and reservations would not be displayed to the user but tool information will be there in the system. | Pass
50 | Tool Management - deactivation and reactivation | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. Go to 'My Tools' of 'Shared Tools' tab, select the 'Tool' which user has deactivated and click on 'Activate'. | System should activate the tool which user had deactivated previously. | Pass
51 | Tool Management - deactivation and reactivation | 1. Borrower must have borrowed the tool | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. Go to 'My Tools' of 'Shared Tools' tab, Click on 'Deactivate tool'. | System shouldn't allow the user to deactivate the tool as user has already borrowed it. | Pass
52 | Tool Management - deactivation and reactivation | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. Go to 'My Tools' of 'Shared Tools' tab. 4. Click on Delete link | System should allow user to delete the tool from the system and deleted tool shouldn't be displayed in the shared borrow tools page. | Pass
53 | Community Statistics | 1. User must have registered to the system. | 1. Go to Tool share online website 2. Click on 'Login' link 3. Enter the valid credentials : Username and Password 4. On main homepage, click on 'community Statistics' to request list of statistics | System should display statistics. | Pass
54 | Notification | 1. User must be registered to the system | 1. Go to Tool share online website 2. Click on 'Login' link 3. Enter the valid credentials : Username and Password 4. Reject tool request or Approve Tool Request or Return Tool. | System should display notification messages incase of approval of tool or rejected of tool or return acknowledgment | Pass
55 | Logout | 1. User must have registered to the system. | 1. Go to Tool share online website 2. On login page, enter the valid credentials of User(Owner) : Username and Password 3. Click on 'Logout' link. | System should allow user to logout and should display login page to the user. | Pass